## Instructions
Weekly team reports are due no later than 5:00 p.m. on Canvas. In addition, you should also send a copy of this report to your Project Leader. To use this report, update your tasks and subtasks on the Team Task Report tab. Those updates will automatically be updated on this page. In addition, make sure you are updating your attendance report in the Attendance Records tab during your weekly meeting. Finally, update the status for the team and each task using the drop down menu. When done, upload this Excel file to Canvas and email it to your Project Leader.

## Weekly Task Report
M:2:I Team Weekly Report
Weekly team reports are due no later than 5:00 p.m.
Project Information
Project Name | MAVRIC
Team name | Science Team
Team Leader Name | Ryan Byrnes
Week Number | 3
Attendance Records
Number of Students Present | 6
Number of students Not Present | 0
Team Status Report
Currently the team is: | On Track
Please put any comments below on the overall status fo the team:
This week, the team met for the first weekly meeting. New team members have taken the M2i lab safety course, have taken the Boyd Lab safety courses, have downloaded Soldiworks, and been introduced to Solidworks. We placed orders for the manufacturing of most of our parts, made revisisons to the two collars, and further improved the spectrometer.
Task Report
Milestone/Task | Due Date | Progress | Status
Martin and Ryan - spectrometer cofiguring and python coding | February | 50% | On Track
Thomas - revise Solidworks model of collar cap | 2018-01-26 | 100% | On Track
Colin - revise Solidworks model of camera and motor collar | 2018-01-26 | 100% | On Track
all - take Boyd lab and M2I safety courses | 2018-01-25 | 100% | On Track
placed order for water jetting rails, 3D printing collection box, new actuator | 2018-01-26 | 50% | Off Track
Nick - completed soil box model | 2018-01-23 | 100% | On Track

## Team Task Chart
M:2:I Team Task Chart
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FOUR
WORK BKDN STRUCTURE | TASK TITLE | TASK OWNER (TBD) | START DATE (TBD) | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Milestone 1 - Manufacturing/Assembly |  |  |  | business days | 0% | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | [5 empty] | 16 | 17 | 18 | 19 | 20
1.1 | first weekly meeting - critique design with new members | all | NA | 2018-01-25 | 1 | 0%: 100%; WEEK 3 R 25: x
1.2 | 3D print collars | M2I lab | 2018-01-22 | 2018-01-29 | 5 | bar: 0%; WEEK 3 M 22 to WEEK 3 F 26
1.3 | water jet rails | Sukup Lab | 2018-01-22 | 2018-01-29 | 5 | 0%: 50%; WEEK 3 M 22: x; WEEK 3 T 23: x; WEEK 3 W 24: x; WEEK 3 R 25: x; WEEK 3 F 26: x
1.4 | mill brackets | Gage |  |  | 5 | 0%: 100%; WEEK 2 M 15: x; WEEK 2 T 16: x; WEEK 2 W 17: x; WEEK 2 R 18: x; WEEK 2 F 19: x
1.6 | cut soil sampler tube | Ryan | NA | 2018-01-20 | 1 | 0%: 100%
1.7 | redesign soil box | Nick | 2018-01-17 | 2018-01-19 | 3 | 0%: 100%; WEEK 2 W 17: x; WEEK 2 R 18: x; WEEK 2 F 19: x
1.8 | 3D print soil box | Nick | 2018-01-22 | 2018-01-29 | 5 | 0%: 50%; WEEK 3 M 22: x; WEEK 3 T 23: x; WEEK 3 W 24: x; WEEK 3 R 25: x; WEEK 3 F 26: x
1.9 | order new actuator | Ryan | 2018-01-22 | 2018-01-29 | 5 | 0%: 100%; WEEK 3 M 22: x; WEEK 3 T 23: x; WEEK 3 W 24: x; WEEK 3 R 25: x; WEEK 3 F 26: x
1.1 | approve motor | Ryan | 2018-01-22 | 2018-01-23 | 2 | 0%: 100%; WEEK 3 M 22: x; WEEK 3 T 23: x
1.11 | 3D print/order standoffs | M2I lab/provider (unresolved) | bar: 0%
1.12 | assemble all parts | all | 2018-01-29 | 2018-02-02 | 5 | bar: 0%; WEEK 4 M 29 to WEEK 4 F 2
1.13 | wiring - on going | collaborate with e team | 2018-02-05 | 2018-02-09 | 5 | bar: 0%; WEEK 5 M 5 to WEEK 5 F 9
1.14 | programming | collaborate with e team | 2018-02-12 | 2018-02-16 | 5 | bar: 0%; WEEK 6 M 12 to WEEK 6 F 16
2 | Milestone 2 - Sensing | Milestone 1 - complete design
2.1 | check moisture sensor | Ryan | NA | 2018-01-22 | 1 | 0%: 100%; WEEK 3 M 22: x
2.2 | check temperature sensor | Ryan | 2018-01-22 | 2018-01-29 | 5 | 0%: 50%; WEEK 3 M 22: x; WEEK 3 T 23: x; WEEK 3 W 24: x; WEEK 3 R 25: x; WEEK 3 F 26: x
2.3 | finalize spectrometer - python script, etc - ongoing | Martin | 2018-01-08 | 2018-02-16 | 30 | 0%: 50%; WEEK 1 M 8: x; WEEK 1 T 9: x; WEEK 1 W 10: x; WEEK 1 R 11: x; WEEK 1 F 12: x; WEEK 2 M 15: x; WEEK 2 T 16: x; WEEK 2 W 17: x; WEEK 2 R 18: x; WEEK 2 F 19: x; WEEK 3 M 22: x; WEEK 3 T 23: x; WEEK 3 W 24: x; WEEK 3 R 25: x; WEEK 3 F 26: x; WEEK 4 M 29: x; WEEK 4 T 30: x; WEEK 4 W 31: x; WEEK 4 R 1: x; WEEK 4 F 2: x; WEEK 5 M 5: x; WEEK 5 T 6: x; WEEK 5 W 7: x; WEEK 5 R 8: x; WEEK 5 F 9: x; WEEK 6 M 12: x; WEEK 6 T 13: x; WEEK 6 W 14: x; WEEK 6 R 15: x; WEEK 6 F 16: x
2.4 | finalize list of on-site tests to perform and collect materials | all | 2018-01-29 | 2018-02-18 | 15 | bar: 0%; WEEK 4 M 29 to WEEK 6 F 16
3 | Milestone 3 - Testing | Milestone 2 - all parts confirmed functional
3.1 | rehearse competition testing - remote and on-site - ongoing | all | 2018-02-19 | 2018-05-06 | 35 | bar: 0%; WEEK 7 M 19 to WEEK 13 F 6

## Dropdown (hidden)
On Track
At Risk
High Risk
Off Track