## Instructions
Weekly team reports are due no later than 5:00 p.m. on Canvas. In addition, you should also send a copy of this report to your Project Leader. To use this report, update your tasks and subtasks on the Team Task Report tab. Those updates will automatically be updated on this page. In addition, make sure you are updating your attendance report in the Attendance Records tab during your weekly meeting. Finally, update the status for the team and each task using the drop down menu. When done, upload this Excel file to Canvas and email it to your Project Leader.

## Weekly Task Report
M:2:I Team Weekly Report
Weekly team reports are due no later than 5:00 p.m.
Project Information
Project Name | MAVRIC
Team name | Science Team
Team Leader Name | Ryan Byrnes
Week Number | 3
Attendance Records
Number of Students Present | 6
Number of students Not Present | 0
Team Status Report
Currently the team is: | On Track
Please put any comments below on the overall status fo the team:
This week, the science team printed the shaft collar. Based on our discussion, we decided it was good to go ahead and print the other collar. We are currently re-evaluating if we want to make the soil collection box out of other materials, based on printing costs. Also, the cap that holds the motor in place will be done on Saturday and printed by Monday. This week, we also received our rails from the water jet, which turned out very nice. Martin continued to develop our python code so that it can take images from the thermal camera and process them to create a emission spectrum chart. He is currently downloading a spectra library from NASA and enabling the program to match outputs with the most similar spectrum from the database.
Task Report
Milestone/Task | Due Date | Progress | Status
Water jet rails | 2018-01-30 | 100% | On Track
Print Collar | 2018-01-30 | 100% | On Track
Design Cap (Saturday) | 2018-02-03 | 50% | On Track
Print Cap (Saturday/Monday) | 2018-02-05 | 0% | On Track
print second collar | 2018-02-02 | 100% | On Track
reconsider soil box | 2018-02-02 | 50% | On Track

## Team Task Chart
M:2:I Team Task Chart
[7 empty] | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR | [14 empty] | PHASE FOUR
WORK BKDN STRUCTURE | TASK TITLE | TASK OWNER (TBD) | START DATE (TBD) | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Milestone 1 - Manufacturing/Assembly |  |  |  | business days | 0% | 8 | 9 | 10 | 11 | 12 | 15 | 16 | 17 | 18 | 19 | 22 | 23 | 24 | 25 | 26 | 29 | 30 | 31 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 1 | 2 | 5 | 6 | 7 | 8 | 9 | 12 | 13 | 14 | 15 | 16 | 19 | 20 | 21 | 22 | 23 | 26 | 27 | 28 | 29 | 30 | 2 | 3 | 4 | 5 | 6 | [5 empty] | 16 | 17 | 18 | 19 | 20
1.1 | first weekly meeting - critique design with new members | all | NA | 2018-01-25 | 1 | 0%: 100%; WEEK 3 R 25: x
1.2 | 3D print collars | M2I lab | 2018-01-22 | 2018-01-29 | 5 | 0%: 100%; WEEK 3 M 22: x; WEEK 3 T 23: x; WEEK 3 W 24: x; WEEK 3 R 25: x; WEEK 3 F 26: x
1.3 | water jet rails | Sukup Lab | 2018-01-22 | 2018-01-29 | 5 | 0%: 100%; WEEK 3 M 22: x; WEEK 3 T 23: x; WEEK 3 W 24: x; WEEK 3 R 25: x; WEEK 3 F 26: x
1.4 | mill brackets | Gage | NA | NA | 5 | 0%: 100%; WEEK 2 M 15: x; WEEK 2 T 16: x; WEEK 2 W 17: x; WEEK 2 R 18: x; WEEK 2 F 19: x
1.6 | cut soil sampler tube | Ryan | NA | 2018-01-20 | 1 | 0%: 100%
1.7 | redesign soil box | Nick | 2018-01-17 | 2018-01-19 | 3 | 0%: 100%; WEEK 2 W 17: x; WEEK 2 R 18: x; WEEK 2 F 19: x
1.8 | 3D print soil box | Nick | 2018-01-22 | 2018-01-29 | 5 | bar: 0%; WEEK 3 M 22 to WEEK 3 F 26
1.9 | order new actuator | Ryan | 2018-01-22 | 2018-01-29 | 5 | 0%: 100%; WEEK 3 M 22: x; WEEK 3 T 23: x; WEEK 3 W 24: x; WEEK 3 R 25: x; WEEK 3 F 26: x
1.1 | approve motor | Ryan | 2018-01-22 | 2018-01-23 | 2 | 0%: 100%; WEEK 3 M 22: x; WEEK 3 T 23: x
1.11 | 3D print/order standoffs | M2I lab/provider (unresolved) | NA | NA | NA | 0%: 100%
1.12 | assemble parts | all | 2018-01-29 | 2018-02-02 | 17 | 0%: 50%; WEEK 4 M 29: x; WEEK 4 T 30: x; WEEK 4 W 31: x; WEEK 4 R 1: x; WEEK 4 F 2: x; WEEK 5 M 5: x; WEEK 5 T 6: x; WEEK 5 W 7: x; WEEK 5 R 8: x; WEEK 5 F 9: x; WEEK 6 M 12: x; WEEK 6 T 13: x; WEEK 6 W 14: x; WEEK 6 R 15: x; WEEK 6 F 16: x; WEEK 7 M 19: x; WEEK 7 T 20: x
1.13 | wiring - on going | collaborate with e team | 2018-02-05 | 2018-02-09 | 12 | bar: 0%; WEEK 5 M 5 to WEEK 7 T 20
1.14 | programming - on going | collaborate with e team | 2018-02-12 | 2018-02-16 | 10 | bar: 0%; WEEK 6 M 12 to WEEK 7 F 23
2 | Milestone 2 - Sensing | Milestone 1 - complete design
2.1 | check moisture sensor | Ryan | NA | 2018-01-22 | 1 | 0%: 100%; WEEK 3 M 22: x
2.2 | check temperature sensor | Ryan | 2018-01-22 | 2018-01-29 | 5 | 0%: 50%; WEEK 3 M 22: x; WEEK 3 T 23: x; WEEK 3 W 24: x; WEEK 3 R 25: x; WEEK 3 F 26: x
2.3 | finalize spectrometer - python script, etc - ongoing | Martin | 2018-01-08 | 2018-02-16 | 30 | 0%: 50%; WEEK 1 M 8: x; WEEK 1 T 9: x; WEEK 1 W 10: x; WEEK 1 R 11: x; WEEK 1 F 12: x; WEEK 2 M 15: x; WEEK 2 T 16: x; WEEK 2 W 17: x; WEEK 2 R 18: x; WEEK 2 F 19: x; WEEK 3 M 22: x; WEEK 3 T 23: x; WEEK 3 W 24: x; WEEK 3 R 25: x; WEEK 3 F 26: x; WEEK 4 M 29: x; WEEK 4 T 30: x; WEEK 4 W 31: x; WEEK 4 R 1: x; WEEK 4 F 2: x; WEEK 5 M 5: x; WEEK 5 T 6: x; WEEK 5 W 7: x; WEEK 5 R 8: x; WEEK 5 F 9: x; WEEK 6 M 12: x; WEEK 6 T 13: x; WEEK 6 W 14: x; WEEK 6 R 15: x; WEEK 6 F 16: x
2.4 | finalize list of on-site tests to perform and collect materials | all | 2018-01-29 | 2018-02-18 | 15 | bar: 0%; WEEK 4 M 29 to WEEK 6 F 16
3 | Milestone 3 - Testing | Milestone 2 - all parts confirmed functional
3.1 | rehearse competition testing - remote and on-site - ongoing | all | 2018-02-19 | 2018-05-06 | 35 | bar: 0%; WEEK 7 M 19 to WEEK 13 F 6

## Dropdown (hidden)
On Track
At Risk
High Risk
Off Track